## Sheet1
Existing Surveys
1. Create a mechanism to retrieve old saved forms from the database.
Purpose: Ensure old saved forms can be accessed by users as-is, without modification.
Steps:
1. Create a query mechanism to fetch forms based on metadata like version, user, formdata, or timestamp.
2. Ensure compatibility with different storage structures (e.g., Legay table data).
3. Add error handling for cases where the form does not exist or is corrupted.
Challenges: Handling legacy formats or inconsistent data structures.
2. Develop a feature to display saved forms in the existing front-end.
Purpose: Provide users with a seamless way to view saved forms using the current UI.
Steps:
1. Add a "View Saved Form" option to the navigation or dashboard.
2. Reuse existing front-end components for consistency in design.
3. Implement fallback designs for unsupported or partially saved forms.
Challenges: Ensuring forms from older versions render properly in the current UI.
3. Add a "Download" button for saved forms with appropriate file formats (e.g., PDF).
Purpose: Allow users to download saved forms for offline access or archival.
Steps:
1. Create a download endpoint that generates PDF or other supported formats.
2. Ensure the download preserves the original form's appearance and data.
3. Add success/error notifications for the download action.
Challenges: Supporting diverse formats while maintaining fidelity across versions.
4. Implement validation to ensure that saved forms are displayed without modification.
Purpose: Guarantee the integrity of saved forms when retrieved and displayed.
Steps:
1. Add backend validation to compare saved data against its schema.
2. Log discrepancies and prevent corrupted forms from being displayed.
3. Provide clear error messages for unsupported or invalid data.
Challenges: Handling edge cases like partially saved forms or schema evolution.
5. Build a mechanism to track whether a form has been used (submitted, published, etc.).
Purpose: Enable the system to distinguish between used and unused forms.
Steps:
1. Add a status field to the form's metadata (e.g., draft, submitted, published).
2. Update this status field during key actions like submission or publishing.
3. Ensure this metadata is accessible and queryable by the system.
Challenges: Ensuring accurate tracking during complex workflows.
6. Develop logic to check and restrict editing of used forms.
Purpose: Prevent users from editing forms that have already been used in production.
Steps:
1. Query the form's status before allowing edit actions.
2. Block edit attempts for forms marked as used with a clear error message.
3. Log restricted edit attempts for audit purposes.
Challenges: Handling scenarios where users attempt unauthorized edits.
New System
7. Enable editing for unused forms using the current template form editor.
Purpose: Allow users to make changes to unused forms for further development.
Steps:
1. Preload the unused form into the editor with all its existing data.
2. Save changes as a new draft version.
3. Validate the edited form to ensure it adheres to current standards.
Challenges: Ensuring backward compatibility with older form versions.
8. Create a save mechanism to store edited forms as new drafts.
Purpose: Preserve original forms while providing an option to save edits as drafts.
Steps:
1. Introduce a draft-saving workflow separate from publishing.
2. Add versioning metadata to distinguish drafts from finalized forms.
3. Implement a retrieval mechanism to view or continue editing drafts.
Challenges: Preventing draft clutter in the database.
9. Build a feature to notify users if editing is restricted for a form.
Purpose: Provide immediate feedback to users attempting to edit restricted forms.
Steps:
1. Display a warning message with reasons for the restriction.
2. Suggest alternative actions (e.g., create a new form).
3. Log these notifications for debugging and compliance tracking.
Challenges: Ensuring the notification does not disrupt other workflows.
10. Implement a comparison tool to display differences between original and edited drafts.
Purpose: Help users identify changes made during editing.
Steps:
1. Retrieve and compare the original and edited versions side by side.
2. Highlight changes using color coding or annotations.
3. Allow users to export the comparison report.
Challenges: Handling complex changes in nested or dynamic form structures.
11. Develop a "recall published version" feature to retrieve old published forms.
Purpose: Enable users to retrieve and reuse published forms.
Steps:
1. Add a "Recall" button in the form management interface.
2. Retrieve the published form data and render it for review.
3. Log recall actions for traceability.
Challenges: Ensuring data consistency between the recalled version and its original state.
12. Create logic to regenerate recalled forms using updated templates.
Purpose: Adapt recalled forms to align with the latest system standards.
Steps:
1. Map old template fields to their updated counterparts.
2. Apply new system constraints without altering the form's intent.
3. Notify users of any incompatible or missing elements.
Challenges: Managing field mapping for significantly changed templates.
13. Implement a review interface for users to compare old and regenerated versions.
Purpose: Allow users to validate changes before reusing recalled forms.
Steps:
1. Display a side-by-side view of the original and regenerated forms.
2. Highlight differences in layout, content, or metadata.
3. Include an approval or rejection workflow.
Challenges: Visualizing complex structural changes effectively.
14. Add notifications for discrepancies between recalled and regenerated versions.
Purpose: Keep users informed about differences in recalled forms.
Steps:
1. Identify and log discrepancies during regeneration.
2. Notify users with detailed descriptions of changes.
3. Allow users to take corrective actions directly from the notification.
Challenges: Balancing detailed notifications with user readability.
15. Provide a mechanism for users to approve or reject regenerated forms.
Purpose: Allow users to maintain control over regenerated forms.
Steps:
1. Create a workflow for approving or rejecting forms.
2. Enable users to add comments or feedback during the process.
3. Log decisions for audit and future reference.
Challenges: Ensuring seamless integration with other workflows.
Nuances and Dependencies
16. Identify and document nuanced cases like partially filled forms or externally shared forms.
Purpose: Ensure edge cases are well-defined and systematically addressed.
Steps:
1. Collaborate with stakeholders to list and describe nuanced scenarios (e.g., shared, partially filled forms).
2. Document expected behaviors and workflows for each scenario.
3. Review with the team to ensure completeness and alignment with business goals.
Challenges: Capturing all possible nuances and their potential variations.
17. Build support for partially filled forms to be viewed in a read-only state.
Purpose: Allow users to view incomplete forms without risking further changes.
Steps:
1. Create a read-only mode that locks fields while retaining data visibility.
2. Add a visual indicator to distinguish partially filled forms.
3. Ensure compatibility with saved drafts or legacy partial data.
Challenges: Properly handling forms with missing or corrupted data.
18. Implement error handling for unsupported forms or deprecated features.
Purpose: Prevent the system from crashing or misbehaving with unsupported forms.
Steps:
1. Introduce error messages for unsupported forms with actionable guidance.
2. Log all occurrences of unsupported features for debugging.
3. Create fallback behavior to minimize disruption to users.
Challenges: Balancing user clarity with technical details in error messages.
19. Develop a fallback "archive view" for deprecated forms to ensure accessibility.
Purpose: Ensure even deprecated forms can be viewed for historical reference.
Steps:
1. Design an archive view with basic display functionality.
2. Clearly label archived forms to prevent confusion with active ones.
3. Provide a download option for archived forms if feasible.
Challenges: Handling inconsistencies in deprecated form formats.
20. Log and report unsupported actions for monitoring and audit purposes.
Purpose: Track unsupported user actions to identify system gaps and improve features.
Steps:
1. Develop a logging mechanism for unsupported actions or features.
2. Aggregate logs into reports for review and prioritization.
3. Use insights from reports to guide system enhancements or user training.
Challenges: Avoiding excessive logging that could overwhelm monitoring systems.
Display and Interaction
21. Enhance the existing front-end to include a "View Saved Form" option in the menu.
Purpose: Simplify navigation for users to access saved forms.
Steps:
1. Add a menu option and ensure it’s contextually placed (e.g., dashboard, side menu).
2. Implement role-based access control to limit visibility where necessary.
3. Test UI changes to ensure usability across devices and screen sizes.
Challenges: Ensuring compatibility with legacy user interfaces.
22. Create a streamlined form download interface with progress indicators.
Purpose: Improve user experience for downloading forms, especially large or complex ones.
Steps:
1. Design a modal or inline progress indicator for downloads.
2. Add notifications for completion or errors during downloads.
3. Optimize download speeds by compressing large files or using asynchronous loading.
Challenges: Maintaining responsiveness for users with slow network connections.
23. Optimize the display of forms to handle large datasets efficiently.
Purpose: Ensure smooth performance when rendering forms with many fields or records.
Steps:
1. Implement pagination or lazy loading for large datasets.
2. Minimize front-end memory usage by fetching data in smaller chunks.
3. Test with extreme data sizes to identify bottlenecks and optimize accordingly.
Challenges: Balancing performance improvements with usability.
24. Add a search and filter functionality for saved forms.
Purpose: Help users quickly locate specific saved forms from a large list.
Steps:
1. Design a search bar and filtering dropdown with common criteria (e.g., date, user, status).
2. Optimize backend queries to ensure fast response times.
3. Allow users to save custom filter presets for repeated use.
Challenges: Ensuring search and filter criteria cover diverse user needs.
25. Ensure accessibility for form viewing and downloading.
Purpose: Make the form system usable for all users, including those with disabilities.
Steps:
1. Test all interfaces for compatibility with screen readers and keyboard navigation.
2. Adjust color schemes and font sizes to meet contrast and readability guidelines.
3. Include accessibility testing as part of regular QA processes.
Challenges: Keeping up with evolving accessibility standards.
Testing and Validation
26. Develop automated tests for form retrieval, display, and download workflows.
Purpose: Ensure key workflows work consistently and without regression.
Steps:
1. Write unit tests for backend retrieval and download logic.
2. Develop end-to-end tests for user interactions with forms.
3. Set up continuous integration pipelines to run tests automatically.
Challenges: Covering all edge cases in test scenarios.
27. Create test cases for editing unused forms and restricting edits for used forms.
Purpose: Validate system behavior for form editing scenarios.
Steps:
1. Write detailed test cases covering all editing conditions (used, unused, draft).
2. Automate tests where feasible to ensure consistency.
3. Review test results regularly to refine edge case handling.
Challenges: Simulating real-world user interactions in tests.
28. Perform usability testing for the recall and regeneration of published forms.
Purpose: Gather feedback on user experience and improve the recall workflow.
Steps:
1. Recruit real users to test the recall and regeneration features.
2. Observe and document pain points during testing sessions.
3. Use findings to prioritize and implement usability improvements.
Challenges: Balancing user preferences with technical feasibility.
29. Conduct performance testing for scenarios involving large or complex forms.
Purpose: Ensure the system performs well under heavy usage or with large forms.
Steps:
1. Simulate high-load scenarios with stress testing tools.
2. Measure response times and identify bottlenecks.
3. Optimize database queries, API endpoints, and front-end rendering as needed.
Challenges: Addressing bottlenecks without overhauling system architecture.
30. Build a feature to track user feedback on form interactions and system behavior.
Purpose: Collect user feedback to guide system improvements.
Steps:
1. Add a feedback button to form-related pages.
2. Develop a backend service to store and aggregate feedback.
3. Analyze feedback data to identify common issues or feature requests.
Challenges: Encouraging meaningful feedback from users.